## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Raghav Kathuria | 14-Jun-2026 | Session configuration should retain product and customer scenario context throughout the support session. | Sprint 1 | Piyush Sapakal | Logical | Updated session handling so configuration is carried into the active conversation flow. | 20-Jun-2026 | Closed | Validated with a new session and configured scenario.
2 | Piyush Sapakal | 28-Jun-2026 | RAG retrieval can return less relevant knowledge when a query contains only generic support terms. | Sprint 2 | Jeya Saravanan | Logical | Improved retrieval validation using semantic similarity together with keyword/context matching. | 05-Jul-2026 | Closed | Relevant knowledge recommendations verified with support queries.
3 | Jeya Saravanan | 12-Jul-2026 | Customer simulator and analysis flow require consistent conversation state across turns. | Sprint 3 | DhanLaxmi | Logical | Updated orchestration/session handling to preserve conversation history and agent outputs. | 18-Jul-2026 | Closed | Multi-turn simulator and analysis flow retested.
4 | DhanLaxmi | 26-Jul-2026 | High-risk customer interactions require escalation handling and representative-assist state to remain synchronized. | Sprint 4 | Varshith.A.MR | Logical | Aligned escalation risk detection with the high-risk handoff and representative-assist workflow. | 01-Aug-2026 | Closed | High-risk escalation flow verified in the support console.
5 | Varshith.A.MR | 09-Aug-2026 | Post-interaction summary and analytics must remain consistent with the completed conversation events. | Sprint 5 | K.V.N.S.Sarvani | Logical | Validated summary, resolution/risk metrics and report generation against session data. | 16-Aug-2026 | Closed | Summary and reporting outputs checked after completed sessions.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others