## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | Study customer support workflows | Must Have | Project scope | Piyush Sapakal | Completed
Sprint 1 | Sprint 1 | US02 | Study coaching methodologies | Must Have | US01 | Piyush Sapakal | Completed
Sprint 1 | Sprint 1 | US03 | Study RAG architecture | Must Have | US01 | Piyush Sapakal | Completed
Sprint 2 | Sprint 2 | US04 | Study multi-agent design patterns | Must Have | US01 | Piyush Sapakal | Completed
Sprint 2 | Sprint 2 | US05 | Design system architecture | Must Have | US02, US03, US04 | Piyush Sapakal; Piyush Sapakal | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours | [23 empty] | Project Duration: 14-Jun-2026 to 29-Aug-2026
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US01 | T01 | Study customer support workflows | 14-Jun-2026 | 15-Jun-2026 | Piyush Sapakal | Research | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Study coaching methodologies | 16-Jun-2026 | 17-Jun-2026 | Piyush Sapakal | Research | Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Study RAG architecture | 18-Jun-2026 | 19-Jun-2026 | Piyush Sapakal | Architecture Study | Completed | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T04 | Study multi-agent design patterns | 20-Jun-2026 | 21-Jun-2026 | Piyush Sapakal | Architecture Study | Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T05 | Design system architecture | 22-Jun-2026 | 24-Jun-2026 | Piyush Sapakal; Piyush Sapakal | System Design | Completed | 8 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Understanding support workflow and architecture | Reviewed workflow, RAG and multi-agent architecture.
Sprint 1 | Day 2 | Agent responsibilities needed alignment | Defined agent roles and orchestration flow.
Sprint 1 | Day 3 | Knowledge-base flow needed validation | Validated knowledge ingestion, chunking and vector indexing.
Sprint 1 | Day 4 | Simulator scenario consistency needed review | Reviewed simulator scenario and conversation flow.
Sprint 1 | Day 5 | System architecture needed team alignment | Finalized system architecture and module dependencies.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 14-Jun-2026 | 27-Jun-2026 | Piyush Sapakal | Start breaking requirements into clear implementation tasks. | Stop delaying architecture decisions. | Continue validating dependencies early. | Architecture and workflow tasks were broken down and reviewed with the team.
2 | Sprint 2 | 28-Jun-2026 | 11-Jul-2026 | Piyush Sapakal | Start testing with varied support scenarios. | Stop relying only on simple inputs. | Continue validating AI outputs end-to-end. | Simulator, intent, sentiment and RAG outputs were reviewed using support scenarios.
3 | Sprint 3 | 12-Jul-2026 | 25-Jul-2026 | Piyush Sapakal | Start integrating coaching and escalation incrementally. | Stop postponing UI integration. | Continue testing risk alerts with the coaching console. | Coaching, escalation monitoring and live console integration were reviewed.
4 | Sprint 4 | 26-Jul-2026 | 08-Aug-2026 | Piyush Sapakal | Start validating reports with complete conversations. | Stop treating reporting separately from session data. | Continue checking analytics against session events. | Session summary, resolution score, analytics and reporting flow were validated.
5 | Sprint 5 | 09-Aug-2026 | 22-Aug-2026 | Piyush Sapakal; Piyush Sapakal | Start documentation alongside implementation. | Stop postponing final documentation. | Continue end-to-end validation and team review. | Documentation, end-to-end validation and final demonstration preparation were completed.